## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking | Risk impact : 1 low - 10 high
Losing time in details | Spent to much times in discussion and implementation of negligible features | 7.5 | 9 | 67.5 | Set fix time for meetings, Start with the important things, Implement details in the end, questionnaire for features | SG
Less Time for Working | Unkown time for project -> other projects need also time | 7.5 | 9 | 67.5 | Start early, work for a defined time every week, plan to finish earlier to have a puffer | ZB
Less Expertise | The team can't get enough expertice for the project. | 3.5 | 7.5 | 26.25 | Spent only fix time, then ask for help | SO
Illness | A person can't work for a longer time (2 weeks) | 3 | 7 | 21 | Starting with the big points and adjust our goals when somebody fails out | SO
Crashing DB | DB will be hacked or crashed | 4 | 4 | 16 | Backups, regulary checks | ZB
Digital Meetings | Digital communication is more complicated as personal. So it's easy to missunderstand the others. And the meetings need more time. | 4.5 | 2 | 9 | Plan with more time, Turn the camera on, Take time for personal exchange | ZB
0
0
0
0